## Sheet1
Tender: "Procurement of Automatic Teller Machines FOR NBP CONVENTIONAL & ISLAMIC BANKING BRANCHES "
NT-08/10/2023-2
Query & Reply
Nos. | Query | NBP UG Response
1 | Reference to Section 6, point 2.08 of said RFP, “ATM facia tempering should have an alert mechanism plus alarm”. | Yes, The ATMs will be required to generate/trigger such alarms/alerts by having relevant mechanism in place.
TPL Response: It is requested to please give us clarification that Alert mechanism will be generated with the existing configuration of the bank?
2 | Section 6, point 7.01, “Audio – Optional high quality public audio and/or sound jack with volume control Barcode Reader (2D) – 2D Barcode supports both 1D and 2D documents”. | This is optional and the bidder may inform us if the same is customizable.
TPL Response: As mentioned in this clause optional, kindly confirm if the bidder does not offer Audio and/or sound jack and barcode reader, so bidder will not be disqualified (as NBP is asking it optional)?
3 | Section 8, point 3, “If any bidder quotes the bid prices other than Pak Rupees, the interbank conversation rate in Pak Rupees (as determined by NBP) on the day of bid financial opening will be considered for calculating total bid amount in Pakistan Rupees (PKR) and for evaluating their bids”. | Here we are referring to the process of bid evaluation only where the relevant bids are compared. In order to maintain uniformity we will have to use a standard rate i.e. as per PPRA regulations.
TPL Response: With reference to the above point, if we get opportunity to win this tender, so kindly process our USD invoices/bills conversion rate in PKR at the time of making payment (current prevailing rate)?
4 | Reference to Heading " Payment terms & conditions Section VIII, Page 69 and point no 2 | Bids maybe submitted in USD. For comparison sake we will use a common yardstick i.e. conversion rate prevailing at the date of bid opening whilst for payment to successful bidders rates prevailaing at the date of invoice would be used.
IPL Response: It is requested to allow the bidder to submit in USD. Applicable Interbank rate would be at the date of invoice.
5 | Reference to heading "Delivery Schedule Section X Page 72 | We cannot acceed to your request as the same is standard and applies to all bidders
IPL Response: It is requested that the delivery timeline to be revised from 24 weeks to 36 weeks.
6 | Quotation for ATMs is required with 1 year warranty and 3 years of service after the warranty? | Yes 1 year warranty + 3 service maintenance
NCR Response: Quotation for ATMs is required with 1 year warranty and 3 years of service after the warranty?
7 | Since the Itemized pricing is required in the Bill of Quantity (Section IX), | Providing Itemized pricing is advsied as the same will be useful when evaluating/comparing different vendors
NCR Response:- Please confirm if the order will be placed for the entire or NBP will evaluate partially and will select partial items as per the BOQ.
8 | Soft copies of the proposal have been requested on CDs as well, | Offcourse use of USB is permissable
NCR Response please let me know if the same can be provided on a USB
9 | In “Section VI”, requirement 4.08 “Security Application must have capability of preventing from zero day attack or unpublished malware and threats and have process based permission policies” – | Please be advised that security applications capable of preventing from zero day attack or unpublished malware and threats EXIST e.g. MS Defender application guard.
NCR Response: Unpublished threats means that the threats that are un known. No vendor can rightfully say that it can protect against some thing unknown, this point is invalid and shall be considered
10 | NCR Corporation is directly participating in the tender. | Please confirm that they do not need to submit a local manufacturer authorization however proof of NCR Pakistan being a representative of Parent company NCR would be required.
NCR Response: NCR believes they don’t need to submit a manufacturer’s authorization form as we are the producers of the ATMs. Please confirm the understanding.
11 | Payment for total amount for ATMs, Software & Licenses implementation (one-time), Software support (03 years) and Hardware (including warranty and Support – 3 years if procured by NBP)- (“Solution Amount”) | Yes, Solution Amount/cost, means the total cost of project
TPL Response: Kindly confirm on Solution Amount/cost, does it mean the total project Amount or the understanding is otherwise?
12 | Clarity Required On Payment Terms | These percentages refer to the total project cost and will be calcuated as stated. The payments will be milestone based. The last 45% will be disbursed on the sucessful completion of the project
TPL Response: 1) Advance payment. 10% of the total project cost will be given to TPL in advance after signing of contract? Point 2), 45% of solution cost after delivery. Let suppose, 50 ATMs (out of 196) delivered in first phase, can we eligible to get payment against 50 ATMs? Point 3), 45% of solution cost after commissioning, installation, training etc. Reference to above point, let suppose 50 ATMs commissioned/installed and training have been given to branches. Will, we able to get the payment against 50 ATMs or after 196 ATMs Go-Live, we will be able to get the payment?
13 | Clarity required on the yearly SLA (HW & SW) cost? | The cost of first four years SLA will be included in the total cost of the project. It will not be charged separately.
TPL Response: What about the yearly SLA (HW & SW) cost, will we get it on per annum basis or it will follow the above payment Milestone?
14 | Clarity Required For Pricing The Dedicated Agile Development Team of 06 resources. | Please quote Man Hours Rate as we will decide on need come basis using this rate.
TPL Response: Same Question for Dedicated Agile Development Team, as the banking is asking for 06 resources. NBP will follow the above payment milestone for 06 resources in “10% advance, 45% after delivery and 45% after Go-live” or otherwise.